## Read me
THE OPEN SHELF · The CARES Collaborative · free to adapt and use
HOW TO USE THIS WORKBOOK
Corrective Action with a Root-Cause Step
What this is
The finding log the protocol describes. One row per finding, from any source, with the instance fix, the root-cause chain, the system fix, and — the step almost always missing — the later check that the fix held.
The three whys
Columns G, H and I are the chain: why did this happen, why was that possible, why was the control missing or failing. If the third answer is a person's name, keep asking. A name is almost never a system cause.
The number that matters
At the foot: findings closed but never effectiveness-checked. A finding closed without that check is a finding you will receive again, and it is the most common gap in this whole process.
What this is not
Not a disciplinary record and not a substitute for your own quality assurance policy or any corrective action plan a regulator requires in its own format.

## 1 Finding log
THE OPEN SHELF · The CARES Collaborative · free to adapt and use
THE REGISTER
One log, every source
Sources: licensing, monitoring, audit, accreditation, complaint, and your own QA sampling. The effectiveness check is a separate, later event with its own date — not part of closure.
# | Date | Source | Finding as written | Instance fix — what was done | Owner | Why did it happen? | Why was that possible? | Why was the control missing or failing? | System fix — what changed | Due | Closed | Check due | Effectiveness check — did it hold? | Notes
1 | 2026-09-03 | Licensing visit | Example — delete. Two personnel files missing a required clearance date | Dates obtained and filed | HR lead | The clearance result was received but not recorded | Recording depended on one person remembering | No gate between clearance and provisioning | Onboarding gate adopted; provisioning blocked until the gate is signed | 2026-10-15 | 2026-10-11 | 2027-01-15
Findings logged
Open — no closure date
Closed
Closed with no root cause recorded
CLOSED BUT NEVER EFFECTIVENESS-CHECKED
Checks that did not hold — the finding will recur