## Read me
THE OPEN SHELF · The CARES Collaborative · free to adapt and use
HOW TO USE THIS WORKBOOK
The Logic Model and SMARTER Objectives Worksheet
What this is
The program design worked in the order that catches errors. Sheet 1 is the chain with the assumption under each link. Sheet 2 is the objectives, one column per SMARTER letter. Sheet 3 pairs each output with the outcome it is not. Sheet 4 is the capacity check, run before launch. Sheet 5 is the measurement plan. Sheet 6 reads from all of them.
Work in this order
1 then 4 then 2. The chain first, because everything else refers to it. The capacity check second, because a No there changes the design rather than the launch plan. The objectives last, because an objective written before the chain exists has nothing to be relevant to.
The two tests
Every outcome traces back to an activity that could plausibly produce it. Every activity is one this organization can staff, supervise, document and evidence — as it is today, not as the proposal describes it.
About the shaded rows
Every shaded italic row is an invented illustration. Delete it before use. None of the figures in this workbook came from a real organization.
What this is not
Not an evaluation. Completing it does not make a program evaluated. Where an independent evaluator is required, this is what you hand them so their work starts from a defined design.

## 1 Logic model
THE OPEN SHELF · The CARES Collaborative · free to adapt and use
LOGIC MODEL
The chain, and the assumption under each link
One row per element. The assumption column is the point: the specific condition that, if false, breaks that step. An assumption you cannot state is a link you have not thought about.
Element | The statement | Where it is evidenced | The assumption it depends on
Input | Two full-time family specialists, 1.0 FTE supervisor, curriculum license | Budget line 4100; approved staffing plan | We can recruit and retain this qualification in this labor market at this rate
Input | In-home delivery capacity — vehicles, mileage, scheduling | Budget lines 5200 and 5210 | Travel time is inside the caseload assumption, not on top of it
Activity | Weekly in-home sessions, twelve-week cycle, one specialist per family | Service model specification section 3 | Families are available weekly at a time a specialist can travel to
Activity | Monthly reflective supervision on every open case | Supervision policy; supervisor duty statement | The supervisor's hours are not already committed elsewhere
Output | Twenty completed twelve-week cycles per year | Case management system, cycle completion field | Attendance holds at a rate high enough to complete; placements do not interrupt
Output | Ninety documented supervision sessions per year | Supervision log | Sessions are documented at the time, not reconstructed
Outcome — short | Caregivers demonstrate specific capability at exit that was absent at intake | Same instrument at intake and exit | The curriculum addresses the actual driver of difficulty for these families
Outcome — medium | Fewer disruptions in the twelve months after exit than in the twelve before | Placement record, matched period | Capability is a material cause of disruption relative to the other causes
Impact | Children in this population experience fewer moves | County placement data, where available
Delete this row before use — invented illustration
Elements stated
LINKS WITH NO ASSUMPTION STATED
Elements with no evidence source
Outcomes and impact stated
Activities stated

## 2 SMARTER objectives
THE OPEN SHELF · The CARES Collaborative · free to adapt and use
SMARTER OBJECTIVES
Objectives written so they can fail
One row per objective. An objective stated as an activity cannot fall short of anything, and therefore teaches nothing. E is Evaluated. R is Revised — not reviewed: a review can conclude nothing needs to happen and still count as done.
# | Objective as written | S — what changes, for whom, from what to what | M — number, source, counting rule | A — basis for believing it reachable | R — the logic model row it serves | T — period and measurement date | E — evaluated when, by whom | R — revision trigger and action | Complete?
1 | By 30 June, 70% of caregivers completing the twelve-week cycle score at least 4 of 6 on the exit capability rubric, against a baseline of 2 of 6 at intake. | Caregiver capability, for families completing the cycle, from 2/6 to 4/6 | Count scoring >=4 at exit / count completing; rubric field in case system | Prior cohort reached 3.6 of 6 without the revised curriculum | Outcome — short: capability demonstrated at exit | Program year to 30 June; measured 15 July | 15 April, program manager, at the two-thirds point | If below 55% at 15 April, curriculum sequence is revised for the next cohort and the change is recorded
Delete this row before use — invented illustration
Objectives written
Complete on all seven letters
NOT MEASURABLE — no number, source or counting rule
Not tied to a logic model row
NO EVALUATION POINT SET
NO REVISION TRIGGER WRITTEN
A revision trigger written after the fact is an explanation. Write it before the program starts.

## 3 Output vs outcome
THE OPEN SHELF · The CARES Collaborative · free to adapt and use
OUTPUT AND OUTCOME
The pair, and what the outcome needs before launch
The third column is the point of the exercise. An outcome with no pre-launch measurement plan is a claim you have decided to make later and will not be able to support.
Output — what you did | Outcome — what changed | What the outcome needs before launch | In place?
Twenty families completed the twelve-week cycle | Caregivers demonstrate capability at exit absent at intake | An intake measure, an exit measure, and the same instrument at both ends | No
Delete this row before use — invented illustration
Pairs stated
OUTCOMES NOT YET MEASURABLE
Outcomes with no measurement plan written

## 4 Capacity check
THE OPEN SHELF · The CARES Collaborative · free to adapt and use
IMPLEMENTATION CAPACITY CHECK
Run this before the design is finished
Scored against the organization as it is today, not as the proposal describes it. A No is not a reason to abandon the design — it is a dependency with a date, and it belongs in the launch plan.
Domain | What has to be true | Yes / Partly / No | If not yet — what has to happen | Date it must be true by
Staffing | The roles exist, the qualification is obtainable at the rate budgeted, and recruitment lead time fits the launch schedule
Supervision | Someone qualified has the hours, and those hours are not already committed
Documentation | The record each contact must produce has a place to live and a standard staff have been shown
Data | Every indicator has a field, a collector, and a collection point inside the ordinary work
Regulatory | Every license, approval, or contract amendment is identified with its lead time
Finance | Unit cost built from the layers, and any gap against the award named
Space and systems | Physical and technical requirements exist or have a dated plan
Referral flow | Reason to believe the eligible population arrives at the volume assumed
Domains scored
Scored Yes
NOT READY — scored No
Partly ready
DEPENDENCIES WITH NO DATE
Do not launch above zero on the third line without a written decision recorded by the board or the executive.

## 5 Measurement plan
THE OPEN SHELF · The CARES Collaborative · free to adapt and use
MEASUREMENT PLAN
Every indicator, settled before launch
One row per indicator. An indicator with no collector and no collection point is a hope. The collection point belongs inside the ordinary work, not beside it.
Indicator | Logic model row it measures | Definition and counting rule | Data source — system and field | Who collects | Collection point | Baseline taken on | Ready?
Capability score at exit | Outcome — short | Count scoring 4 or more of 6 at exit / count completing the cycle | Case system, rubric field | Family specialist | Exit session, before the file closes |  | No
Delete this row before use — invented illustration
Indicators planned
NOT READY TO COLLECT
No named collector
BASELINE NOT TAKEN

## 6 Design readiness
THE OPEN SHELF · The CARES Collaborative · free to adapt and use
ONE PAGE FOR THE BOARD
Design readiness
Every figure here is read from the other sheets. Nothing on this page is typed.
Elements in the chain | Inputs through impact
Links with no assumption stated | Each one is a step nobody has examined
Objectives written
Objectives complete on all seven letters
Objectives with no evaluation point | Nothing will examine these before the period ends
Objectives with no revision trigger | Written afterward it becomes an explanation
Outcomes not yet measurable | Claims you cannot support
Capacity domains scored No | Dependencies, not disqualifiers
Dependencies with no date | These are the ones that surprise you in month two
Indicators with no baseline taken | After launch a baseline cannot be recovered
The revision point | The date the first cohort's experience is read against the design and the design is changed.
The discontinuation standard | What result, sustained over what period, would mean this program should change substantially or stop.